## Listing
No | Module | Deliverables | Status | Remarks
1 | USER | User List | Done | ok
2 |  | Add User | Done | Where to setup the password? - Auto generated and sent to users .. Contact number should be optional - Done If Role is Admin, do we have to select customer or by default all customer? - If admin no need to select customer . By default - all customer
3 |  | Edit | Done | ok
4 |  | Delete | Done | oK
5 |  | Duplicate Validation | Done | ok
6 |  | Send Password via Email | - | cant connect to wms@vfreight.com SMTP
7 |  | Link to Customer | Done | ok
8 |  | isActive Validation | Done | ok
9 | Roles | Role Access List | Done | ok
10 |  | Add Role | Done | ok
11 |  | View Access | Done | ok
12 |  | Save Access | Done | ok
13 |  | Delete | Done | Deletion should not allow if there are user associated to the role - Done
14 |  | Duplicate Validation | Done | ok
15 | Customer | Customer List | Done | ok
16 |  | Add customer | Done | ok
17 |  | Edit | Done | ok
18 |  | Delete | Done | ok
|  | Allocation Strategy | Done | Drow-down should be fixed to - FIFO, FEFO and Per Batch/Lot Number If FEFO, need to key-in minimum days
19 |  | Duplicate Validation | Done | ok
20 | SKU | SKU List | Done | ok
21 |  | Add Sku | Done | Please include - Weight (in Kg), Length, Width, Height (in cm), CBM, Remarks
22 |  | Edit | Done | ok
23 |  | Delete | Done | ok
24 |  | Duplicate Validation | Done | ok
25 |  | Customerkey dropdown | Done | ok
26 | Location | Location List | Done | ok
27 |  | Add | Done | ok
28 |  | Edit | Done | ok
29 |  | Delete | Done | ok
|  | Location Type | Done | ok
|  | Location Status | Done | ok
30 |  | Duplicate Validation | Done | ok
31 | PID | Pallet ID List | Done | ok. Deleted
32 |  | Add | Done
33 |  | Edit | Done
34 |  | Delete | Done
35 |  | Duplicate Validation | Done
| UOM | Pallet ID List | Done | ok
|  | Add | Done | ok
|  | Edit | Done | ok
|  | Delete | Done | ok
|  | Duplicate Validation | Done | ok
36 | Receiving | Duplicate Validation | - | Testing in progress
37 |  | List Pending | Done | ok
38 |  | List Partially Received | Done | ok
39 |  | List Fully Received | Done | Change the label from "Edit Receipt" to "Fully Received" in view action form
40 |  | Save | Done | ok
41 |  | New | Done | User can only see associated customer (in Customer drop-down) based on User profile setup PO, DR, Waybill and warehouse ref should be alphanumeric Can you confirm if Location is not part of detail entry?
42 |  | Cancel | Done | ok
43 |  | Receive | Done | ok
44 |  | Finalize | Done | ok
45 | Issuance | List Pending | Done | Rename "Order List" to "Order List (Open Order)"
46 |  | List Allocated | Done | Not yet tested since inventory cannot move to good location Please consider "Unallocate button"
47 |  | List Fully Picked | Done | Need to allocated first
48 |  | List Finalized | - | Change to Shipped instead of Finalized
49 |  | Update | - | Where and what is this update?
50 |  | Cancel | - | ok
51 | Issuance Entry | Retrieve | - | ok
52 |  | New | - | Customer Orderno and Customer Code should be alphanumeric/varchar UOM should have drop down
53 |  | Save | - | ok
54 |  | Cancel | - | ok
55 |  | Add Row | - | ok
56 | STO | STO Trans List | -
57 | Putaway | New | - | ok
58 |  | Save | - | not yet working please consider splitting/dividing of qty if possible
59 |  | Cancel | - | ok
60 | Stock Transfer Entry | New | - | Cannot add SKU and other detail info
61 |  | Save | - | Not yet tested
62 |  | Cancel | - | Not yet tested
63 | Adjustments | Adjustment Trans List | - | ok
64 | Adjustment Entry | New | - | ok
65 |  | Save | - | ok
66 |  | Cancel | - | ok
67 | Inventory Report | Inventory Report List | - | not yet fully tested since status change have to be validated
68 |  | Generate Excel | - | ok
69 | Inventory per Expiry | Inventory Report List | - | wrong label and no expiration date in the report
70 |  | Generate Excel | - | to be checked later
71 | Inventory per Product Name | Inventory Report List | - | ok
72 |  | Generate Excel | - | ok
73 | Inventory per Location | Inventory Report List | - | ok
74 |  | Generate Excel |  | ok
75 | Receiving Report | Report List | - | Where to key-in Receipt Date? "Received by" data cannot search
76 |  | Generate Excel | - | ok
77 |  | Generate PDF | - | ok
78 | Inventory Issuance | Issuance List | - | Should include Order Status
79 |  | Generate Excel | - | ok
80 | Damaged Report | Damaged List | - | Dependent on putaway.
81 |  | Generate PDF | - | to be checked later
82 | Delivery Receipt | Generate List | - | No Delivery Receipt found
83 |  | Generate PDF | - | to be checked later
84 | Pick List | Pick List | - | No report found
85 |  | Generate PDF | - | to be checked later
86 | Ageing Report | Ageing Report | - | ok
87 |  | Generate Excel | - | ok
88 | Sign Out | Clear Session | - | ok
89 | Change Password |  | - | ok
90 | Forgot Password |  | - | email doesn't work yet. To be checked later
91 | Mini Chat |  | Done | How does the user know if the other user is online or offline? Is this public or private chat? How does the user send message to certain user?
92 | Change Theme |  | Done | I don’t know where to change theme?
93 | Deploy to wms.vfeight.com |  | - | ok
94 | Dashboard |  | - | Good to have but least priority in dev

## General
General Questions |  | Remarks
1 | How to manage multiple/selected customer in single user access? Is this possible or one user one customer only?
2
3