## Sheet1
Module | Deliverables | Status | Remarks
USER | User List | Done
| Add User | Done
| Edit | Done
| Delete | Done
| Duplicate Validation | Done
| Send Password via Email |  | cant connect to wms@vfreight.com SMTP
| Link to Customer | Done
| isActive Validation | Done
Roles | Role Access List | Done
| Add Role | Done
| View Access | Done
| Save Access | Done
| Delete | Done
| Duplicate Validation | Done
Customer | Customer List | Done
| Add customer | Done
| Edit | Done
| Delete | Done
| Duplicate Validation | Done
SKU | SKU List | Done
| Add Sku | Done
| Edit | Done
| Delete | Done
| Duplicate Validation | Done
| Customerkey dropdown | Done
Location | Location List | Done
| Add | Done
| Edit | Done
| Delete | Done
| Duplicate Validation | Done
PID | Pallet ID List | Done
| Add | Done
| Edit | Done
| Delete | Done
| Duplicate Validation | Done
Duplicate Validation
| List Pending | Done
| List Partially Received | Done
| List Fully Received | Done
| Save | Done
| New | Done
Cancel
Receive
Finalize
Issuance | List Pending | Done
| List Allocated | Done
| List Fully Picked | Done
List Finalized
Update
Cancel
Issuance Entry | Retrieve
New
Save
Cancel
Add Row
STO | STO Trans List
Putaway | New
Save
Cancel
Stock Transfer Entry | New
Save
Cancel
Adjustments | Adjustment Trans List
Adjustment Entry | New
Save
Cancel
Inventory Report | Inventory Report List
Generate Excel
Inventory per Expiry | Inventory Report List
Generate Excel
Inventory per Name | Inventory Report List
Generate Excel
Inventory per Location | Inventory Report List
Generate Excel
Receiving Report | Report List
Generate Excel
Generate PDF
Inventory Issuance | Issuance List
Generate Excel
Damaged Report | Damaged List
Generate PDF
Delivery Receipt | Generate List
Generate PDF
Pick List | Pick List
Generate PDF
Ageing Report | Ageing Report
Generate Excel
Sign Out | Clear Session
Change Password
Forgot Password
Mini Chat |  | Done
Change Theme |  | Done
Deploy to wms.vfeight.com