## Sheet1
No | Module | Deliverables | Status | Remarks
1 | USER | User List | Done
2 |  | Add User | Done
3 |  | Edit | Done
4 |  | Delete | Done
5 |  | Duplicate Validation | Done
6 |  | Send Password via Email | - | cant connect to wms@vfreight.com SMTP
7 |  | Link to Customer | Done
8 |  | isActive Validation | Done
9 | Roles | Role Access List | Done
10 |  | Add Role | Done
11 |  | View Access | Done
12 |  | Save Access | Done
13 |  | Delete | Done
14 |  | Duplicate Validation | Done
15 | Customer | Customer List | Done
16 |  | Add customer | Done
17 |  | Edit | Done
18 |  | Delete | Done
19 |  | Duplicate Validation | Done
20 | SKU | SKU List | Done
21 |  | Add Sku | Done
22 |  | Edit | Done
23 |  | Delete | Done
24 |  | Duplicate Validation | Done
25 |  | Customerkey dropdown | Done
26 | Location | Location List | Done
27 |  | Add | Done
28 |  | Edit | Done
29 |  | Delete | Done
30 |  | Duplicate Validation | Done
31 | PID | Pallet ID List | Done
32 |  | Add | Done
33 |  | Edit | Done
34 |  | Delete | Done
35 |  | Duplicate Validation | Done
36 | Receiving | Validate Qty Received | -
37 |  | List Pending | Done
38 |  | List Partially Received | Done
39 |  | List Fully Received | Done
40 |  | Save | Done
41 |  | New | Done
42 |  | Delete | Done
43 |  | Receive | Done
45 | Issuance | List Pending | Done
46 |  | List Allocated | Done
47 |  | List Fully Picked | Done
49 |  | Update | Done
52 |  | New | Done
53 |  | Save | Done
54 |  | Cancel | -
55 |  | Add Row | Done
56 | STO | STO Trans List | -
57 | Putaway | Putaway List | Done
58 |  | New | Done
59 |  | Save | Done
60 | Stock Transfer Entry | New | -
61 |  | Save | -
62 |  | Cancel | -
63 | Adjustments | Adjustment Trans List | -
64 | Adjustment Entry | New | -
65 |  | Save | -
66 |  | Cancel | -
67 | Inventory Report | Inventory Report List | -
68 |  | Generate Excel | -
69 | Inventory per Expiry | Inventory Report List | Done
70 |  | Generate Excel | -
71 | Inventory per Name | Inventory Report List | -
72 |  | Generate Excel | -
73 | Inventory per Location | Inventory Report List | -
74 |  | Generate Excel
75 | Receiving Report | Report List | -
76 |  | Generate Excel | -
77 |  | Generate PDF | -
78 | Inventory Issuance | Issuance List | -
79 |  | Generate Excel | -
80 | Damaged Report | Damaged List | -
81 |  | Generate PDF | -
82 | Delivery Receipt | Generate List | -
83 |  | Generate PDF | -
84 | Pick List | Pick List | -
85 |  | Generate PDF | -
86 | Ageing Report | Ageing Report | -
87 |  | Generate Excel | -
88 | Sign Out | Clear Session | -
89 | Change Password |  | -
90 | Forgot Password |  | -
91 | Mini Chat |  | Done
92 | Change Theme |  | Done
93 | Deploy to wms.vfeight.com |  | -
94 | Dashboard |  | -