## Listing
No | Module | Deliverables | Status | Remarks
1 | USER | User List | Done | ok
2 |  | Add User | Done | Where to setup the password? - Auto generated and sent to users .. Contact number should be optional - Done If Role is Admin, do we have to select customer or by default all customer? - If admin no need to select customer . By default - all customer
3 |  | Edit | Done | ok
4 |  | Delete | Done | oK
5 |  | Duplicate Validation | Done | ok
6 |  | Send Password via Email | - | cant connect to wms@vfreight.com SMTP
7 |  | Link to Customer | Done | ok
8 |  | isActive Validation | Done | ok
9 | Roles | Role Access List | Done | ok
10 |  | Add Role | Done | ok
11 |  | View Access | Done | ok
12 |  | Save Access | Done | ok
13 |  | Delete | Done | Deletion should not allow if there are user associated to the role - Done
14 |  | Duplicate Validation | Done | ok
15 | Customer | Customer List | Done | ok
16 |  | Add customer | Done | ok
17 |  | Edit | Done | ok
18 |  | Delete | Done | ok
|  | Allocation Strategy | Done | Drow-down should be fixed to - FIFO, FEFO and Per Batch/Lot Number If FEFO, need to key-in minimum days
19 |  | Duplicate Validation | Done | ok
20 | SKU | SKU List | Done | ok
21 |  | Add Sku | Done | Please include - Weight (in Kg), Length, Width, Height (in cm), CBM, Remarks
22 |  | Edit | Done | ok
23 |  | Delete | Done | ok
24 |  | Duplicate Validation | Done | ok
25 |  | Customerkey dropdown | Done | ok
26 | Location | Location List | Done | ok
27 |  | Add | Done | ok
28 |  | Edit | Done | ok
29 |  | Delete | Done | ok
|  | Location Type | Done | ok
|  | Location Status | Done | ok
30 |  | Duplicate Validation | Done | ok
31 | PID | Pallet ID List | Done | ok. Deleted
32 |  | Add | Done
33 |  | Edit | Done
34 |  | Delete | Done
35 |  | Duplicate Validation | Done
| UOM | Pallet ID List | Done | ok
|  | Add | Done | ok
|  | Edit | Done | ok
|  | Delete | Done | ok
|  | Duplicate Validation | Done | ok
37 |  | List Pending | Done | ok
38 |  | List Partially Received | Done | ok
39 |  | List Fully Received | Done | Change the label from "Edit Receipt" to "Fully Received" in view action form - Done
40 |  | Save | Done | ok
41 |  | New | Done | User can only see associated customer (in Customer drop-down) based on User profile setup PO, DR, Waybill and warehouse ref should be alphanumeric - Done Can you confirm if Location is not part of detail entry? - Yes sir, default location is STAGE
42 |  | Cancel | Done | ok
43 |  | Receive | Done | ok
44 |  | Finalize | Done | ok
45 | Issuance | List Pending | Done | Rename "Order List" to "Order List (Open Order)" - Done
46 |  | List Allocated | Done | Not yet tested since inventory cannot move to good location - Use putaway Please consider "Unallocate button" - There's unallocate button on Allocated list
47 |  | List Fully Picked | Done | Need to allocated first - allocate order on order list ( Open Order )
48 |  | List Finalized | - | Change to Shipped instead of Finalized - Done
49 |  | Update | - | Where and what is this update? - If Open and not yet allocated you can update order header or details
50 |  | Cancel | - | ok
51 | Issuance Entry | Retrieve | - | ok
52 |  | New | - | Customer Orderno and Customer Code should be alphanumeric/varchar - Done UOM should have drop down - Done
53 |  | Save | - | ok
54 |  | Cancel | - | ok
55 |  | Add Row | - | ok
56 | STO | STO Trans List | -
57 | Putaway | New | - | ok
58 |  | Save | - | not yet working - working please consider splitting/dividing of qty if possible - use stock transfer? Else will add qty field
59 |  | Cancel | - | ok
60 | Stock Transfer Entry | New | - | Cannot add SKU and other detail info - Done
61 |  | Save | - | Not yet tested
62 |  | Cancel | - | Not yet tested
63 | Adjustments | Adjustment Trans List | - | ok
64 | Adjustment Entry | New | - | ok
65 |  | Save | - | ok
66 |  | Cancel | - | ok
67 | Inventory Report | Inventory Report List | - | not yet fully tested since status change have to be validated
68 |  | Generate Excel | - | ok
69 | Inventory per Expiry | Inventory Report List | - | wrong label and no expiration date in the report - Done
70 |  | Generate Excel | - | to be checked later
71 | Inventory per Product Name | Inventory Report List | - | ok
72 |  | Generate Excel | - | ok
73 | Inventory per Location | Inventory Report List | - | ok
74 |  | Generate Excel |  | ok
75 | Receiving Report | Report List | - | Where to key-in Receipt Date? - On Search "Received by" data cannot search - Done
76 |  | Generate Excel | - | ok
77 |  | Generate PDF | - | ok
78 | Inventory Issuance | Issuance List | - | Should include Order Status - Done
79 |  | Generate Excel | - | ok
80 | Damaged Report | Damaged List | - | Dependent on putaway.
81 |  | Generate PDF | - | to be checked later
82 | Delivery Receipt | Generate List | - | List and pdf is on Issuance -> Shipped. Should I create a separate link on reports?
83 |  | Generate PDF | - | to be checked later
84 | Pick List | Pick List | - | List and pdf is on Issuance -> Picked. Should I create a separate link on reports?
85 |  | Generate PDF | - | to be checked later
86 | Ageing Report | Ageing Report | - | ok
87 |  | Generate Excel | - | ok
88 | Sign Out | Clear Session | - | ok
89 | Change Password |  | - | ok
90 | Forgot Password |  | - | email doesn't work yet. To be checked later - Already created a ticket to allow SMTP email
91 | Mini Chat |  | Done | How does the user know if the other user is online or offline? Is this public or private chat? How does the user send message to certain user? This is for public all user can see the message. We can remove this one :D
93 | Deploy to wms.vfeight.com |  | - | ok
94 | Dashboard |  | - | Good to have but least priority in dev

## General
General Questions |  | Remarks
1 | How to manage multiple/selected customer in single user access? Is this possible or one user one customer only?
2
3