## Sheet1
Module | Deliverables | Status | Remarks
USER | User List | Done
| Add User | Done
| Edit | Open
| Delete | Open
| Duplicate Validation | Open
| Send Password via Email | Open
| Link to Customer | Open
| isActive Validation | Open
Roles | Role Access List | Done
| Add Role | Done
| View Access | Done
| Save Access | Done
| Delete | Open
| Duplicate Validation | Open
Customer | Customer List | Done
| Add customer | Done
| Edit | Open
| Delete | Open
| Duplicate Validation | Open
SKU | SKU List | Done
| Add Sku | Done
| Edit | Open
| Delete | Open
| Duplicate Validation | Open
| Customerkey dropdown | Open
Location | Edit | Open
| Delete | Open
| Duplicate Validation | Open
PID | Pallet ID List | Done
| Add | Done
| Edit | Open
| Delete | Open
| Duplicate Validation | Open
Receiving | Receiving List | Open
| Add | Open
| Edit | Open
| Delete | Open
| Duplicate Validation | Open
Receiving Entry | Save | Open
| Retrieve | Open
| New | Open
| Cancel | Open
| Receive | Open
| Finalize | Open
Issuance | Issuance List | Open
| List Open | Open
| List Allocated | Open
| List Fully Picked | Open
| List Finalized | Open
| Update | Open
| Cancel | Open
Issuance Entry | Retrieve | Open
| New | Open
| Save | Open
| Cancel | Open
| Add Row | Open
STO | STO Trans List | Open
Putaway | New | Open
| Save | Open
| Cancel | Open
Stock Transfer Entry | New | Open
| Save | Open
| Cancel | Open
Adjustments | Adjustment Trans List | Open
Adjustment Entry | New | Open
| Save | Open
| Cancel | Open
Inventory Report | Inventory Report List | Open
| Generate Excel | Open
Inventory per Expiry | Inventory Report List | Open
| Generate Excel | Open
Inventory per Name | Inventory Report List | Open
| Generate Excel | Open
Inventory per Location | Inventory Report List | Open
| Generate Excel | Open
Receiving Report | Report List | Open
| Generate Excel | Open
| Generate PDF | Open
Inventory Issuance | Issuance List | Open
| Generate Excel | Open
Damaged Report | Damaged List | Open
| Generate PDF | Open
Delivery Receipt | Generate List | Open
| Generate PDF | Open
Pick List | Pick List | Open
| Generate PDF | Open
Ageing Report | Ageing Report | Open
| Generate Excel | Open
Sign Out | Clear Session | Open
Change Password |  | Open
Forgot Password |  | Open
Send Password |  | Open
Mini Chat |  | Done
Change Theme |  | Open